## Project
Project
Basic Info
Field | Value
Name | mikuproject開発
Title | mikuproject開発
Author
Company
StartDate | 2026-03-16
FinishDate | 2026-04-01
CurrentDate | 2026-03-23 09:00:00
StatusDate | 2026-03-23 09:00:00
Settings
CalendarUID | 1
MinutesPerDay | 480
MinutesPerWeek | 2400
DaysPerMonth | 20
ScheduleFromStart | ○
OutlineCodes | 0
WBSMasks | 0
ExtendedAttributes | 0

## Tasks
Tasks
Task List
UID | ID | Name | OutlineLevel | OutlineNumber | WBS | Start | Finish | Duration | PercentComplete | PercentWorkComplete | Milestone | Summary | Critical | CalendarUID | Predecessors | Notes
1 | 1 | 基盤整備 | 1 | 1 | 1 | 2026-03-16 09:00:00 | 2026-03-17 18:00:00 | PT0H0M0S | 100 |  | ー | ○
2 | 2 | 着手 | 2 | 1.1 | 1.1 | 2026-03-16 | 2026-03-16 | PT0H0M0S | 100 |  | ○ | ー
3 | 3 | 初期実装（MS Project XML 調査・基軸フォーマット選定・内部モデルの概要確定） | 2 | 1.2 | 1.2 | 2026-03-16 09:00:00 | 2026-03-16 18:00:00 | PT0H0M0S | 100 |  | ー | ー
4 | 4 | round-trip拡張（MS Project XML → 内部JSON形式 → MS Project XML の往復対応） | 2 | 1.3 | 1.3 | 2026-03-17 09:00:00 | 2026-03-17 18:00:00 | PT0H0M0S | 100 |  | ー | ー
5 | 5 | 架空検討フェーズ【架空】 | 1 | 2 | 2 | 2026-03-19 09:00:00 | 2026-03-25 18:00:00 | PT0H0M0S | 25 |  | ー | ○
6 | 6 | ユーザー操作フローの見直し【架空】 | 2 | 2.1 | 2.1 | 2026-03-19 09:00:00 | 2026-03-23 18:00:00 | PT0H0M0S | 50 |  | ー | ー
7 | 7 | 画面構成の再整理【架空】 | 2 | 2.2 | 2.2 | 2026-03-24 09:00:00 | 2026-03-25 18:00:00 | PT0H0M0S | 0 |  | ー | ー
8 | 8 | XLSX / UI 強化 | 1 | 3 | 3 | 2026-03-27 09:00:00 | 2026-03-28 18:00:00 | PT0H0M0S | 0 |  | ー | ○
9 | 9 | GitHub リポジトリ独立化 | 2 | 3.1 | 3.1 | 2026-03-27 | 2026-03-27 | PT0H0M0S | 0 |  | ○ | ー
10 | 10 | MS Project XML と XLSX の相互変換・round-trip実装 | 2 | 3.2 | 3.2 | 2026-03-27 09:00:00 | 2026-03-27 18:00:00 | PT0H0M0S | 0 |  | ー | ー
11 | 11 | XLSXレイアウト再設計・再整理 | 2 | 3.3 | 3.3 | 2026-03-28 09:00:00 | 2026-03-28 18:00:00 | PT0H0M0S | 0 |  | ー | ー
12 | 12 | リリース | 1 | 4 | 4 | 2026-03-29 09:00:00 | 2026-03-29 18:00:00 | PT0H0M0S | 0 |  | ー | ○
13 | 13 | v1.0 リリース | 2 | 4.1 | 4.1 | 2026-03-29 | 2026-03-29 | PT0H0M0S | 0 |  | ○ | ー

## Resources
Resources
Resource List
UID | ID | Name | Type | Initials | Group | MaxUnits | CalendarUID | StandardRate | OvertimeRate | CostPerUse | Work | ActualWork | RemainingWork
1 | 1 | Mikuku | 0 | M | Development | 1 | 1

## Assignments
Assignments
Assignment List
UID | TaskUID | TaskName | ResourceUID | ResourceName | Start | Finish | Units | Work | ActualWork | RemainingWork | PercentWorkComplete
1 | 3 | 初期実装（MS Project XML 調査・基軸フォーマット選定・内部モデルの概要確定） | 1 | Mikuku | 2026-03-16 09:00:00 | 2026-03-16 18:00:00 | 1 | PT8H0M0S |  |  | 100
2 | 4 | round-trip拡張（MS Project XML → 内部JSON形式 → MS Project XML の往復対応） | 1 | Mikuku | 2026-03-17 09:00:00 | 2026-03-17 18:00:00 | 1 | PT8H0M0S |  |  | 100

## Calendars
Calendars
Calendar List
UID | Name | IsBaseCalendar | BaseCalendarUID | WeekDays | Exceptions | WorkWeeks
1 | Standard | ○ |  | 7 | 1 | 0

## NonWorkingDays
NonWorkingDays
Calendar Exceptions
CalendarUID | Index | CalendarName | Name | Date | FromDate | ToDate | DayWorking
1 | 1 | Standard | 春分の日 | 2026-03-20 | 2026-03-20 | 2026-03-20 | ー

## Options
BooleanChoice | Meaning
○ | true
ー | false